## Sheet1
Heyy Cab Customer App Reviews
DATE | Task Need to Do | Description | Assigned To
2019-08-21 | App Version Missing | Need to place the version no below the logo | Ramesh
2019-08-21 | Country Selection | Get the country selection as same in Android else make the flag size little bit smaller | Ramesh
2019-08-21 | In signup Screen keyboard overlapping Date picker | When entered the last name and selected DOB Dropdown, the Keyboard should hide. Bcz its hiding the date picker dialog | Ramesh
2019-08-21 | OTP Screen | Replicate the design same as in Android | Ramesh
2019-08-21 | Support Missing | Support Module is Not Implemented | Ramesh
2019-08-21 | My Enquiries Missing | My Enquiries Module is not Implemented | Ramesh
2019-08-21 | Personal Details Section | Replicate the design same as in Android | Ramesh
2019-08-21 | Remove Payment Details | Payment Details in Customer App is temp disable for now. So hide it | Ramesh
2019-08-21 | Ride Booking Module | The Drop location need to be confirmed before booking the ride in map. Refer Android For Reference | Ramesh
2019-08-21 | Route Polyline Color | Route Polyline Color should be in Blue Color | Ramesh
2019-08-21 | Marker Design Change | Change the Default Marker to Designed Marker for Pickup and Drop Location. Contact Design Team For Icons | Ramesh
2019-08-21 | Ride Type Disabling | Based on the Ride Estimated kms, the ride type needs to be Enabled and Disabled. | Ramesh
2019-08-21 | City Rides Error | The Cab is showing in the City Ride in Android but not showing in iOS Device. Debug and Correct it with Help of Ananthan | Ramesh and Ananthan
2019-08-21 | Designs | Check the Design Changes side by side with Android | Ramesh
2019-08-21 | Login Issues | Unable to login using the same Credentials using in Android | Ramesh and Ananthan
2019-08-21 | Cab Icon List Issue | Available nearedt Cab Should Be visible in the Home Page | Ramesh
Discontinuing the Test Process. Unable to Test bzc of Cab not showing