## Sheet1
| To be completed by: | ANANTHAN
Deadline:
% done | DESCRIPTION OF THE ISSUE | Development Remarks | RAISED BY | Issue Type | CLIENT NAME | DUE BY | REMARKS | STATUS OF THE ISSUE | DEVELOPER | TESTED BY | REMARK | ISSUE REOPENED | ISSUE REOPENED DATE | ESTIMATED TIME LINE
APP ISSUES
0% | While creating a new customer from the app, need to include password validation. As of now its allowing less than 6 characters but while logging in, password validation is there
0% | In ticket enquiry, next to amount, "USD" text is missing |  | VICHU |  | ANGKOR WAT APP | ANANTHAN | Need API Support
0% | In ticket enquiry, once after selecting multiple dates, in ticket date need to change the date view. Like for example, if the dates has been chosen like 15,18,20th May, in ticket date its showing like 15to20 |  | VICHU |  | ANGKOR WAT APP | ANANTHAN | Share me the format how it needs to be displayed
0% | In ticket enquiry, for 3 days and 7 days, need drag option for date selection |  | VICHU |  | ANGKOR WAT APP | ANANTHAN | we can use drag option but we cant select different dates. So we put the option like this to select random days for example: now the calendar we can select 12, 14,16 if we keep dragging it will be like selecting 1, 13, 14.
0% | Once dates has been selected in the calendar, and again if calendar has been viewed, already selected dates has been disappeared. |  | VICHU |  | ANGKOR WAT APP | ANANTHAN
0% | In booking history,. If multiple dates are chosen, need to show the dates which has been selected by the customers. As of now first date only showing |  | VICHU |  | ANGKOR WAT APP | ANANTHAN | Back end Work
0% | In ticket enquiry, after selecting "7 days", app is getting log out automatically |  | VICHU |  | ANGKOR WAT APP | ANANTHAN
0% | In ticket enquiry calendar, its showing only the current month. Need to show all the months or else should show the next month like if customers are booking the date at the end of the month, next month calendar should show to select the respective dates |  | VICHU |  | ANGKOR WAT APP | ANANTHAN | for this purpose only we kept a text box in backend that indicates how many dates should be displayed for selection. If you give 50 days. It will show 2 months calendar
0% | In account module, uploaded photo is disappearing and its not reflecting in the web side also |  | VICHU |  | ANGKOR WAT APP | ANANTHAN | Need API support
0% | in application if wrong password entered - app closes - remember forget password isnt done ?? |  | VICHU |  | ANGKOR WAT APP | ANANTHAN | Here its working fine, if password is wrong it says Invalid Password and forgot password also working good. Kindly share me the credentials and other testing methods done
WEB ISSUES
0% | Need masters for Angkor tips, Booking conditions and Privacy policy |  | VICHU |  | ANGKOR WAT APP | ANANTHAN
0% | Need people master and their group permissions |  | VICHU |  | ANGKOR WAT APP | ANANTHAN
0% | In notification module, only webside booking datas are showing. App side booking datas are not reflecting |  | VICHU |  | ANGKOR WAT APP | ANANTHAN
0% | In notification module, need to show the date and timestamp |  | VICHU |  | ANGKOR WAT APP | ANANTHAN
0% | In notification module, Export excel is not functional. Its showing 404 error while exporting |  | VICHU |  | ANGKOR WAT APP | ANANTHAN
0% | In booking module, after searching data through date filter option, its leading to notification module page |  | VICHU |  | ANGKOR WAT APP | ANANTHAN
0% | In booking module, Need to add "Show" filter and "Booking type" filter option |  | VICHU |  | ANGKOR WAT APP | ANANTHAN
0% | In booking module, Need to show Newly booked datas on the top. As of now datas are showing below the old data |  | VICHU |  | ANGKOR WAT APP | ANANTHAN
0% | In booking module, after searching data through date filter option, its leading to notification module page |  | VICHU |  | ANGKOR WAT APP | ANANTHAN
0% | In booking module, need scroll option at the bottom to see all the data |  | VICHU |  | ANGKOR WAT APP | ANANTHAN
0% | In booking module, need timestamp with date |  | VICHU |  | ANGKOR WAT APP | ANANTHAN
0% | In add booking module, need to validate "No of tickets". Its allowing alphanumeric |  | VICHU |  | ANGKOR WAT APP | ANANTHAN
0% | In add booking module, need to add "remove" option to remove the wrongly uploaded photo |  | VICHU |  | ANGKOR WAT APP | ANANTHAN
0% | In add customer module, need to validate "Mobile" field. Its allowing alphanumeric and also it should allow 7 to 14 characters. As of now its allowing n number of characters |  | VICHU |  | ANGKOR WAT APP | ANANTHAN
0% | In add customer module, need to add "remove" option to remove the wrongly uploaded photo |  | VICHU |  | ANGKOR WAT APP | ANANTHAN
0% | In add customer module, Mandatory fields need to be indicated with * symbol |  | VICHU |  | ANGKOR WAT APP | ANANTHAN
0% | In add customer module, keep the email field before the password field under login details |  | VICHU |  | ANGKOR WAT APP | ANANTHAN
0% | In customer module, timstamp is showing wrong. |  | VICHU |  | ANGKOR WAT APP | ANANTHAN
0% | In customer module, Need to add "Show" filter option |  | VICHU |  | ANGKOR WAT APP | ANANTHAN
0% | In customer module, for customer list need active/inactive option |  | VICHU |  | ANGKOR WAT APP | ANANTHAN
0% | In customer module,under customer list while deleting the customer, need a popup option like "Are u sure want to delete the customer?" As of now its deleting the data directly. |  | VICHU |  | ANGKOR WAT APP | ANANTHAN
0% | In settings, need to validate child age limit, adult price, child price and calendar show number fields. As of now its allowing alphanumeric |  | VICHU |  | ANGKOR WAT APP | ANANTHAN
0% | In package module, under pakage list, active/inactive is not functional |  | VICHU |  | ANGKOR WAT APP | ANANTHAN
0% | In package module, under package list, while deleting the package, need a popup option like "Are u sure want to delete this package?"As of now its deleting the data directly. |  | VICHU |  | ANGKOR WAT APP | ANANTHAN
0% | In package module, under add package, need to validate package days, calendar show number and package price. As of now its allowing alphanumeric |  | VICHU |  | ANGKOR WAT APP | ANANTHAN
0% | Notification status bar is not functional on the top right corner |  | VICHU |  | ANGKOR WAT APP | ANANTHAN
0% | While seletcing "verification" option, its showing 404 error |  | VICHU |  | ANGKOR WAT APP | ANANTHAN | removed. Not used
0% | While selecting "account" option, logged in profile data is showing but it should show the complete data so that we need people masters |  | VICHU |  | ANGKOR WAT APP | ANANTHAN | I need explain